## RACI Matrix
Task | Project Manager | Business Analyst | UI UX Designer | Developer | Tester | Client
Define functional requirements | A | R | I | I | I | C
Stakeholder identification | A | R | I | I | I | C
Create user flow | C | R | A | I | I | C
Design wireframes | I | C | R | I | I | A
Design UI layout | I | C | R | I | I | A
Plan system architecture | A | C | I | R | I | I
Setup development environment | A | I | I | R | I | I
Develop frontend | I | I | C | R | I | A
Develop backend | I | I | I | R | I | A
Integrate system | A | I | I | R | C | I
Implement core features | A | I | I | R | C | I
Unit testing | I | I | I | R | A | I
Integration testing | I | I | I | R | A | I
System testing | I | I | I | C | R | A
Bug fixing | A | I | I | R | C | I
Deployment | A | I | I | R | C | I
Go Live | A | I | I | R | C | A
Manage Go Live issues | A | I | I | R | C | I
Project closure workshop | R | I | I | I | I | A
Closure documentation | R | C | I | I | I | A
Approve closure | I | I | I | I | I | A
Legend
R | Responsible
A | Accountable
C | Consulted
I | Informed