## Tasks
# | Incident / Risk | Lesson Learnt | Action Item | Owner | Status
1 | Payment integration Failure | Early testing of third-party integrations is critical | Perform integration testing in early phases and maintain backup gateway | Backend Developer | Not Started
2 | Server Performance Issue | Infrastructure planning must consider peak load scenarios | Implement load testing and auto-scaling before deployment | DevOps Enginner | In Process
3 | User Login Issues | Authentication systems must be validated thoroughly | Strengthen testing for login and session management | Tech Lead | Not Started
4 | Worker Verification Delay | Manual processes slow down onboarding | Introduce partial automation in verification process | Operations Manager | Not Started
5 | UI UX Inconsistency | User experience directly impacts engagemen | Conduct usability testing and collect user feedback early | UI UX Desiginer | In Process
6 | Data Security Risk | Security must be integrated from the beginning, not later | Apply encryption, secure APIs, and regular security audits | Security Enginner | In Process
7 | Low User Adoption Risk | Product success depends on user trust and awareness | Plan marketing campaigns and onboarding incentives | Product Owner | Not Started
8 | Requirement Clarity Issue | Unclear requirements lead to delays and rework | Define detailed requirements and acceptance criteria early | Project Manager | In Process