## Project Risks
Project Name |  | Kaamdost
Last Updated |  | 2026-03-23
# | Risk Title | Risk Description / Impact | Identified Date | Risk Category | Risk Sub-Category | Status | Owner | Risk Rating | Possible Mitigation | Date Closed
001 | App Development Delay | Development may be delayed due to lack of technical skills or unclear requirements. | 2026-03-23 | Project | Technical | Open | Developer | High | 1. Define clear requirements 2. Use Agile sprints 3. Take mentor guidance
002 | User Registration Issues | Users may face issues during signup or login, affecting user experience. | 2026-03-23 | Technical | Backend | Open | Developer | Medium | 1. Test login system thoroughly 2. Use secure authentication 3. Fix bugs quickly
003 | Poor UI/UX Design | App design may not be user-friendly, leading to low engagement. | 2026-03-23 | Project | Design | Closed | Design | Medium | 1. Use simple UI 2. Take user feedback 3. Improve design iterations
004 | Low User Adoption | Users may not trust or use the platform initially. | 2026-03-23 | Organisation | Market | Open | Product owner | High | 1. Marketing campaign 2. Offer initial incentives 3. Build trust through reviews
005 | Payment Integration Failure | Payment system may fail or not work properly. | 2026-03-23 | Technical | Integration | Open | Developer | Critical | 1. Use trusted payment gateway 2. Perform testing 3. Backup payment option
006 | Data Security Risk | User data may be exposed or hacked. | 2026-03-23 | Security | Data Protection | Open | Developer | Critical | 1. Use encryption 2. Secure APIs 3. Regular security testing
007 | Worker Profile Fraud | Fake workers may create profiles, reducing trust. | 2026-03-23 | Oprational | User Management | Open | Admin | High | 1. Aadhaar verification 2. Manual approval 3. Rating system
008 | Server Downtime | App may go offline due to server issues. | 2026-03-23 | Technical | Infrastructure | Open | DevOps | High | 1. Use cloud hosting 2. Monitor uptime 3. Backup server

## Summary
Issues Summary – Kaamdost
Total Open Issues | 5
Total New Issues | 0
Total Issue On-Hold | 0
Total Unresolved Issues | 9
Total Issues with Severity "Critical" | 2
Total Issues with Priority "Urgent" | 3
Total Issues marked "High" | 4