## Dashboard
Project Cost Summary
Description | Planned | Actual | Variance
Resource | 16500 | 13500 | -3000
Software | 5000 | 4500 | -500
Hardware | 3000 | 2750 | -250
Other | 3000 | 2400 | -600
Total | 27500 | 23150 | -4350
Resource Costs
Software, Hardware and Other Costs
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.

## Resource Costs
# | Resource Name | Resource Type | Daily Rate | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | Planned Cost | Actual Cost
|  |  |  | 2026-03-10 | 2026-03-10 | 2026-04-10 | 2026-04-10 | 2026-05-11 | 2026-05-11 | 2026-06-11 | 2026-06-11 | 2026-07-12 | 2026-07-12 | 2026-08-12 | 2026-08-12 | 2026-09-12 | 2026-09-12 | 2026-10-13 | 2026-10-13 | 2026-11-13 | 2026-11-13 | 2026-12-14 | 2026-12-14 | 2027-01-14 | 2027-01-14 | 2027-02-14 | 2027-02-14
1 | Tiku | Developer | 250 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | 3 | 2 | 2 |  | 1 | [11 empty] | 3500 | 3000
2 | Pankaj | Developer | 250 | 2 | 1 | 2 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | [12 empty] | 3000 | 2500
3 | Amit | QA | 250 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | [8 empty] | 2000 | 1500
4 | Prince | QA | 250 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 |  | 1 | 1 | [12 empty] | 1500 | 1000
5 | Komal | Analyst | 250 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [9 empty] | 2000 | 1750
6 | Ajay | Analyst | 250 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [9 empty] | 2000 | 1750
7 | Ravi | Project Manager | 250 |  |  |  | 1 |  |  | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | [8 empty] | 1250 | 1000
8 | anna | Support | 250 | [10 empty] | 2 | 2 | 2 | 1 | 1 | 1 | [8 empty] | 1250 | 1000
9 | [27 empty] | 0 | 0
10 | [27 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 0 | 0
[28 empty] | 16500 | 13500
3000
Formulas:
A = [P]
P = [P]+31
P = [A]+31

## Software Costs
# | Software Cost Description | Planned | Licensing | Consultaion | Setup | Project Total | Ongoing | Actual | Licensing | Consultaion | Setup | Project Total | Ongoing
[7 empty] | Per Annum | [5 empty] | Per Annum
1 | Could based leave system |  | 800 | 500 | 700 | 2000 |  |  | 800 | 500 | 500 | 1800
2 | Business Rules Engine |  | 1200 | 800 | 1000 | 3000 | 900 |  | 1000 | 900 | 800 | 2700 | 900
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
|  |  | 2000 | 1300 | 1700 | 5000 | 900 |  | 1800 | 1400 | 1300 | 4500 | 900

## Hardware Costs
# | Hardware Cost Description | Planned | Cost | Setup Fees | FST | Project Total | Ongoing | Actual | Cost | Setup Fees | FST | Project Total | Ongoing
[7 empty] | Per Annum | [5 empty] | Per Annum
1 | Database servers |  | 1200 | 200 | 100 | 1500 | 200 |  | 1100 | 150 | 100 | 1350 | 180
2 | Additional Desktops(5 nos) |  | 800 | 100 | 100 | 1000 | 150 |  | 750 | 100 | 100 | 950 | 120
3 | 16 GB RAM for servers (5 nos) |  | 500 |  |  | 500 | 100 |  | 450 | 0 |  | 450 | 80
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
|  |  | 2500 | 300 | 200 | 3000 | 450 |  | 2300 | 250 | 200 | 2750 | 380

## Others
# | Item Decscription | Planned | Actual
1 | User Manual | 750 | 450
2 | Team Dinner | 2250 | 1950
|  | 3000 | 2400

## Vendor
No | Vendor Cost Description | Planned (USD) | Actual (USD)
1 | Payment Gateway Service (Integration + Transaction Fees) | 1500 | 1300
2 | Cloud Hosting Provider (AWS / Azure services) | 1200 | 1100
3 | Third-party API Services (SMS, Email Notifications) | 800 | 700
4 | Security & Authentication Services | 500 | 400
| TOTAL | 4000 | 3500

## Config
Resource Type | Planned | Actual | Software Expense Categories | Hardware Expense Categories | Category | Planned | Actual | Ongoing
Developer | 6500 | 5500 |  |  | Software | 5000 | 4500 | 900
Analyst | 4000 | 3500 |  |  | Hardware | 3000 | 2750 | 380
Project Manager | 1250 | 1000 | Licensing | Cost | Others | 3000 | 2400
QA | 3500 | 2500 | Consultaion | Setup Fees | Vendor | 4000 | 3500
Support | 1250 | 1000 | Setup | FST
| 16500 | 13500