## Dashboard
Project Name : Kaamdost
About Project | Overall health
Green
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
Kaamdost is a digital platform that connects users with local service providers, offering seamless service discovery, booking, and management. The project follows a hybrid delivery approach to ensure flexibility, efficiency, and high-quality outcomes.
Budget : 30000 USD
Current Phase: Development
digital platform that connects users with local service providers, offering seamless service discovery, booking, and management. The project follows a hybrid delivery approach to ensure flexibility, efficiency, and high-quality outcomes.

## Status
Project Name |  | Kaamdost |  | Project Manager |  | Ravi Raj |  | Date | 2026-03-10
Project Health Card | [7 empty] | Green
Schedule |  | Amber | Development phase is behind planned progress. Risk of timeline slippage identified.
Budget |  | Green | Project is under budget with a positive variance of 18500
Resources |  | Amber | Resource allocation is uneven and impacted by availability issues.
Quality |  | Red | Number of unresolved defects has exceeded acceptable threshold. Immediate action required.
Scope |  | Amber | Scope is stable but 2 change requests are pending approval.
Risks |  | Amber | Project risks are identified and under monitoring but require mitigation actions.
Issues |  | Red | There are 4 high priority issues impacting project progress.
Change Mgt |  | Green | Change management plan is being prepared and aligned with project needs.
Project Schedule
No | Task |  |  | Start | Finish | Progress | Projected Date |  | Concerns
1 | Analysis |  |  | 2026-03-30 | 2026-04-17 | 100 | 2026-04-17 |  | No
2 | Build |  |  | 2026-04-20 | 2026-05-12 | 66 | 2026-05-16 |  | No
3 | Development |  |  | 2026-05-13 | 2026-06-16 | 29 | 2026-06-22
3 | Quality Assurance |  |  | 2026-06-17 | 2026-07-15 | 10 | 2026-07-20 |  | No
4 | User Acceptance Testing |  |  | 2026-07-16 | 2026-07-25 | 0 | 2026-07-28 |  | No
5 | Production |  |  | 2026-07-26 | 2026-07-28 | 0 | 2026-07-30 |  | No
6 | Support |  |  | 2026-07-29 | 2026-07-31 | 0 | 2026-08-02 |  | No
Project Financials
No | Item |  |  | Planned Spend |  | Actual Spend |  | Variance
1 | Resourcing Costs |  |  | 15000 |  | 13500 |  | 1500
2 | Software Costs |  |  | 5000 |  | 4200 |  | 800
3 | Hardware Costs |  |  | 3000 |  | 2500 |  | 500
4 | Vendor Costs |  |  | 4000 |  | 3200 |  | 800
5 | Other Expenses |  |  | 3000 |  | 2400 |  | 600
Totals |  |  |  | 30000 |  | 25800 |  | 4200
Top 5
No | Type | Description |  |  |  | Status | Owner |  | Due
1 | Risk | Technical architecture risk identified but mitigation not fully closed |  |  |  | Amber | Neel |  | 2026-04-24
2 | Issue | Unplanned team leaves impacting delivery velocity |  |  |  | Red | Wale |  | 20/052026
3 | Decision | Technical architecture approval pending and blocking progress |  |  |  | Amber | Sam |  | 2026-04-30
4 | Dependency | External hardware dependency still open and not resolved |  |  |  | Amber | Ram |  | 2026-06-05
5 | Change Request | Pending approvals required to control scope impact |  |  |  | Amber | Jam |  | 2026-04-13

## Data
Task Information |  | Budget Information |  |  | Schedule
Task Type | No. | Month | Planned | Actual | Task | Duration
On Track | 8 | Resourcing | 15000 | 13500 | Analysis | 21
Delayed | 8 | Software Costs | 5000 | 4200 | Build | 11
Not Started | 10 | Hardware Cost | 3000 | 2500 | Development | 17
|  | Vendor Cost | 4000 | 3200 | Quality Assurance | 4
Risks |  | Other Expenses | 3000 | 2400 | User Acceptence Testing | 13
High | 5 |  |  |  | Production | 6
Medium | 8 |  |  |  | Support | 12
Low | 9
Issues
High | 2
Medium | 1
Low |  | Total | 30000 | 25800
Decisions Actions Changes
Decisions Pending | 1
Actions Pending | 5
Change Requests Pending | 2
Project Status
Red | 2
Green | 4
Amber | 2